## Gantt Chart
No_objective | Objectives | Task | Sub-task | Sub-task_no | Comment |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Delay | Comment
[6 empty] | status | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |  | W2March3
1 | Yolo | physical setup | bought equipment | 1 |  | done
|  |  | assambling setup | 2 | viscous and colour fluid | done
|  |  | Testing setup | 3 |  | done
|  | Basic Yolo model (model 1) for clasification of regime of flow | Collect image and train model on colab | 4 | investigate Yolo model, loss matrix, and parameters on yolo, minimize background effect, select good condition of viscosity for image, wc position, use previous experience from previous projects | done
|  |  | Basic model | 5 | 3 stage of fluid | done
|  |  | testing model | 6 |  | done
|  |  | connecting WC/smart phone to model | 7 | option | done
|  |  | deploy model on cloud | 8 | option: 1) pack trained Yolo model - azure platform. 2) deploy directly on cloud and use smartphone or wifiWC | ongoing | [25 empty] | Literature review, not finish
|  | Advanced Yolo model (model 2) for count bubble rate | method to count bubble | 9 | basic model + count bubble | done
|  |  | Collect image and train model on colab | 10 |  | done
|  |  | testing model | 11 |  | done | [25 empty] | result: api
|  |  | deploy model on cloud | 12 |  | ongoing | [25 empty] | Literature review, not finish
|  | Document - transfer | Document - transfer | 13 |  | not start
2 | Kafka_Pyspark | Kafka-Pyspark concept | Data - Kafka - Database - Pyspark - dashboard | 14 |  | ongoing
|  | Kafka | Kafka workflow development | 15 | code on open-source, python | ongoing
|  | Pyspark | develop notebook on pyspark | 16 | connect kafka to pyspark, transfer code from Raman project to pyspark notebook | not start
|  |  | implement ML model to pyspark | 17 | transfer packed ML model from Raman project to pyspark notebook | not start
|  | time series Database | InfluxDB (industrial database) | 18 |  | not start
|  |  | SQLDB | 19 |  | not start
|  | dashboard | develop dashboard from opensource | 20 | Check real-time option? | not start
|  |  | Power BI | 21 | use the power BI dashboard from previous project | not start
|  | implement on cloud | VM | 22 | select right VM on Azure | not start
|  |  | connecting all part | 23 |  | not start
|  |  | Test platform | 24 |  | not start
3 | Azure | Azure workflow | Data from python - database - Iothub -function app - Databrick - delta lake - power BI | 25 | use platform and model from Raman project | not start
4 | Write the thesis | structure of thesis |  | 26 |  | not start
|  | draft of thesis |  | 27 |  | not start
|  | finial thesis |  | 28 |  | not start
|  | Presentation and demo for defend |  | 29 |  | not start
5 | Support to paper publication |  |  | 30 |  | not start
6 | Meeting |  |  | 32 |  | not start | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
7 | Group meeting |  |  | 33 |  | not start